## Sheet1
Design | [5 empty] | Coding | [5 empty] | Testing
| Chris Lockhart | Chris Boyle | Steven Shofner | Jason Spruill | Total |  | Chris Lockhart | Chris Boyle | Steven Shofner | Jason Spruill | Total |  | Chris Lockhart | Chris Boyle | Steven Shofner | Jason Spruill | Total
August | [5 empty] | August | [5 empty] | August
SRS | 0 | 0 | 0 | 0 | 0 | Engine | 0 | 0 | 0 | 0 | 0 | Engine | 0 | 0 | 0 | 0 | 0
SDD | 0 | 0 | 0 | 0 | 0 | Game | 0 | 0 | 0 | 0 | 0 | Game | 0 | 0 | 0 | 0 | 0
Coding Design | 10 | 0 | 0 | 0 | 10 | GUI | 0 | 0 | 0 | 0 | 0 | GUI | 0 | 0 | 0 | 0 | 0
Test Planning | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 5 | 0 | 0 | 5
Meeting | 10 | 10 | 10 | 10 | 40 | Input | 0 | 0 | 0 | 0 | 0 | Input | 0 | 0 | 0 | 0 | 0
Total | 20 | 10 | 10 | 10 | 50 | Total | 0 | 0 | 0 | 0 | 0 | Total | 0 | 5 | 0 | 0 | 5
September | [5 empty] | September | [5 empty] | September
SRS | 4 | 20 | 15 | 5 | 44 | Engine | 73.6 | 0 | 0 | 0 | 73.6 | Engine | 10 | 0 | 0 | 0 | 10
SDD | 4 | 0 | 0 | 0 | 4 | Game | 0 | 0 | 0 | 0 | 0 | Game | 0 | 5 | 0 | 0 | 5
Coding Design | 40 | 30 | 9 | 10 | 89 | GUI | 23 | 0 | 9 | 0 | 32 | GUI | 0 | 0 | 5 | 0 | 5
Test Planning | 0 | 2 | 0 | 5 | 7 | Networking | 0 | 50 | 0 | 0 | 50 | Networking | 0 | 5 | 0 | 0 | 5
Meeting | 5 | 5 | 5 | 5 | 20 | Input | 0 | 0 | 0 | 20 | 20 | Input | 0 | 0 | 0 | 5 | 5
Total | 53 | 57 | 29 | 25 | 164 | Total | 96.6 | 50 | 9 | 20 | 175.6 | Total | 10 | 10 | 5 | 5 | 30
October | [5 empty] | October | [5 empty] | October
SRS | 0 | 0 | 0 | 0 | 0 | Engine | 48.6 | 0 | 0 | 5 | 53.6 | Engine | 10 | 0 | 0 | 0 | 10
SDD | 4 | 20 | 10 | 8 | 42 | Game | 5 | 26 | 0 | 0 | 31 | Game | 0 | 10 | 0 | 0 | 10
Coding Design | 40 | 11 | 51 | 5 | 107 | GUI | 13 | 0 | 46 | 0 | 59 | GUI | 0 | 0 | 5 | 0 | 5
Test Planning | 5 | 5 | 5 | 5 | 20 | Networking | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0
Meeting | 5 | 5 | 5 | 5 | 20 | Input | 0 | 20 | 0 | 30 | 50 | Input | 0 | 0 | 0 | 5 | 5
Total | 54 | 41 | 71 | 23 | 189 | Total | 66.6 | 46 | 46 | 35 | 193.6 | Total | 10 | 10 | 5 | 5 | 30
November | [5 empty] | November | [5 empty] | November
SRS | 0 | 0 | 0 | 0 | 0 | Engine | 20 | 20 | 10 | 0 | 50 | Engine | 0 | 0 | 1 | 1 | 2
SDD | 0 | 0 | 0 | 0 | 0 | Game | 20 | 15 | 0 | 0 | 35 | Game | 0 | 0 | 1 | 1 | 2
Coding Design | 0 | 0 | 0 | 0 | 0 | GUI | 0 | 0 | 0 | 15 | 15 | GUI | 0 | 0 | 1 | 1 | 2
Test Planning | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0
Meeting | 20 | 20 | 20 | 20 | 80 | Input | 5 | 5 | 5 | 0 | 15 | Input | 0 | 0 | 1 | 1 | 2
Total | 20 | 20 | 20 | 20 | 80 | Total | 45 | 40 | 15 | 15 | 115 | Total | 0 | 0 | 4 | 4 | 8
December | [5 empty] | December | [5 empty] | December
SRS | 0 | 0 | 0 | 0 | 0 | Engine | 10 | 5 | 0 | 5 | 20 | Engine | 0 | 0 | 1 | 1 | 2
SDD | 0 | 0 | 0 | 0 | 0 | Game | 10 | 5 | 0 | 0 | 15 | Game | 0 | 0 | 1 | 1 | 2
Coding Design | 0 | 0 | 0 | 0 | 0 | GUI | 0 | 5 | 5 | 0 | 10 | GUI | 0 | 0 | 1 | 1 | 2
Test Planning | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0 | Networking | 0 | 0 | 0 | 0 | 0
Meeting | 10 | 10 | 10 | 10 | 40 | Input | 0 | 5 | 0 | 0 | 5 | Input | 0 | 0 | 1 | 1 | 2
Total | 10 | 10 | 10 | 10 | 40 | Total | 20 | 20 | 5 | 5 | 50 | Total | 0 | 0 | 4 | 4 | 8
Total | 157 | 138 | 140 | 88 | 523 | Total | 228.2 | 156 | 75 | 75 | 534.2 | Total | 20 | 25 | 18 | 18 | 81
Name | Aug. | Sept. | Oct. | Nov | Dec
Jason S. | 10 | 50 | 63 | 39 | 19
Steven S. | 10 | 43 | 122 | 39 | 19
Chris B. | 15 | 117 | 97 | 60 | 30
Chris L. | 20 | 159.6 | 130.6 | 65 | 30