## Sheet1
Task | Assigned | Hours | Hours So Far: | Status:
Research Game Engine | Chris L./Steven | 5 | 0 | Working
Design Game Loop | Chris L./Steven | 3 | 0
Implement Game Loop | Chris L./Steven | 10 | 0
Implement State Management | Chris L./Steven | 16 | 0
Implement Scene Management | Chris L./Steven | 24 | 0
Design Input Management | Jason | 10 | 0 | Working
Implement Input Management | Jason | 10 | 0
Game Screen | Chris L./Steven | 40 | 0
Implement Game Logic | Chris L./Steven | 40 | 0
Multi-Player | Chris B. | 5 | 0
Research Networking API | Chris B. | 5 | 0 | Working
Implement Network Management | Chris B. | 10 | 0
Design Server Logic | Chris B. | 10 | 0
Implement Logger | Chris B. | 10 | 0
Respond to Client Requests | Chris B. | 5 | 0
Chat | Chris B. | 5 | 0
AI | Chris B. | 32 | 0
Implement Sound | Jason | 15 | 0
Documentation | Jason | 20 | 0
Total Hours: |  | 275 | 0
| Chris L./Steven | 138
| Jason | 55
| Chris B. | 82
| Total Hours: | 275